## Requests
Title | Problem | Wanted outcome | Workaround today | Urgency | Asked by | People on it | Status | Effort | Decision | Reason
Search the board by request title | Customers scroll the whole list to check for a duplicate and file one anyway | A search box above the list that matches words in a title | Browser find on page, which only searches what is loaded | Annoying, works around it | Support | 41 | In progress | 2 | Doing | Cheap and it stops the duplicates
Export voters and what they pay as a CSV | Finance asks once a quarter and somebody copies it by hand | A download button on the voters list | Copying rows into a spreadsheet | Annoying, works around it | Finance | 28 | In review | 1 | Doing | One day of work for a job that happens four times a year
Single sign on for the public board | Enterprise buyers ask in the first call and the deal stalls | Sign in with the company identity provider | Nothing, the deal waits | Blocking | Sales | 62 | Suggested | 5 | Next quarter | The largest item on the list and the one that unblocks the most revenue
Dark theme for the public board | The board is bright next to a product that is not | A dark version of the public page | Living with it | Nice to have | Customers | 19 | Suggested | 3 | Later | Asked for often and by nobody who would leave over it
Merge duplicate requests | Two rows for one idea split the votes and hide the real demand | Merging two requests and adding the votes together | Closing one and asking people to vote again | Annoying, works around it | Product | 35 | Completed | 2 | Done | Shipped in 2.4
Threaded comments | Long discussions are hard to follow on a busy request | Replies nested under a comment | Reading top to bottom | Nice to have | Customers | 7 | Suggested | 3 | Refused | Comment threads on a feedback board turn into a forum nobody moderates